## Campaign Goals
| SMART Goals (Specific, Measurable, Assignable, Relevant, Time-Based) | Success Owner | How are we tracking success?
Center Enrollment Growth | 5% monthly growth in number enrolled for each center | Jake/MarComm | FY22 Enrollment tracker
Digital Acquisiton | Increase leads to ELCD by 20% each month (compared to FY21 leads) | Jake/MarComm | Caldera Forms Data
Continuous Improvement | Report metrics, leads, and enrollment status to ELCD each month at monthly MarComm calls | Jake/Marcomm | Monthly Call Reports

## Calendar
| Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
Strategy | July | August | September | October | November | December | January | February | March | April | May | June
Driect Mail | Quarter 1 July: Direct Mail Drop 1A; Quarter 1 August: Direct Mail Drop 1C; Quarter 3 March: Direct Mail Drop 2A; Quarter 4 April: Direct Mail Drop 2B
Direct Mail Drop 1B
Facebook | Quarter 1 July: Promoted Post 1 (Enrollment Promotion); Quarter 2 November: Promoted Post 2 (Activity Pack - Lead Aquisition); Quarter 2 December: Promoted Post 2 (Activity Pack - Lead Aquisition); Quarter 4 April: Promoted Post 3 (Promotional Video)
Google | $600 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $600 Monthly Ad Budget Running | $500 Monthly Ad Budget Running | $500 Monthly Ad Budget Running
Parent Referral | Quarter 1 July: 60 Day Campaign 1 Kickoff; Quarter 1 August: 60 Day Campaign 1 Ends; Quarter 2 October: 60 Day Campaign 2 Kickoff; Quarter 2 November: 60 Day Campaign 2 Ends
App Outreach | Quarter 1 July: 60 Day Campaign 1 Kickoff; Quarter 1 August: 60 Day Campaign 1 Ends; Quarter 2 October: 60 Day Campaign 2 Kickoff; Quarter 2 November: 60 Day Campaign 2 Ends; Quarter 4 April: 60 Day Campaign 3 Kickoff; Quarter 4 May: 60 Day Campaign 3 Ends
Targeting Previously Enrolled Families | Quarter 1 July: Center Directors email past families directly; Quarter 1 August: Center Directors email past families directly; Quarter 1 September: Center Directors email past families directly

## Launch Planning
Due by date: | Strategy Planning | Mailers | Digital Ads
Week of June 14 |  | Begin mailer draft design
Address check with Brian
2021-06-22 | Meet with Rosanne and Shanta in Monthly Check-In
Week of June 21 |  | Mailer design check-in
Mailer copy created
Rescheduled: meet with Rosanne about her region
Website landing page review
Website landing page ELCD center review
Google ad's created
2021-06-29 |  | ELCD design check-in with drafts from Miriam
2021-06-30 |  |  | Website updated
2021-07-01 | Marcomm review of mailers and digital ads
Rosanne/Shanta review of mailers
Digital Ads running
2021-07-02 |  | Designs to Brian
Addresses to Brian

## Parent Referral Program
| English | Spanish | Mandarin |  |  | English |  | Spanish |  | Mandarin
Rosanne |  |  |  |  | Rosanne
Busy Bee |  |  |  |  | Busy Bee |  |  | 50 | 50.49
Bridgeport |  |  |  |  | Bridgeport |  | 50.49
Edgewater |  |  |  |  | Edgewater |  | 50.49
TOTAL |  |  |  | TOTAL COST | TOTAL |  |  | 50 |  |  | TOTAL COST
COST |  |  |  | 198.47 | COST
Shanta |  |  |  |  | Shanta
Joliet |  |  |  |  | Joliet | 100 | 56.99 | 100 | 56.99
Elgin |  |  |  |  | Elgin | 100 | 56.99 | 100 | 56.99
Aurora |  |  |  |  | Aurora | 100 | 56.99 | 100 | 56.99
TOTAL |  |  |  | TOTAL COST | TOTAL | 300 |  | 300 |  | 0 | TOTAL COST
COST |  |  |  | 168.98 | COST |  | 170.97 |  | 170.97 |  | 341.94

## Enrollment Gaps
Region 1
| BP1 | [7 empty] | BP2 | [7 empty] | Edgewater | [7 empty] | Busy Bee | [6 empty] | Busy Bee Home Visiting
| Current Capacity | Current Enrollment | Difference in slots | Infants-Toddlers – GAP | 2YO – GAP | 3-5YO – GAP | School Age – GAP |  | Current Capacity | Current Enrollment | Difference in slots | Infants-Toddlers – GAP | 2YO – GAP | 3-5YO – GAP | School Age – GAP |  | Current Capacity | Current Enrollment | Difference in slots | Infants-Toddlers – GAP | 2YO – GAP | 3-5YO – GAP | School Age – GAP |  | Current Capacity | Current Enrollment | Difference in slots | Infants-Toddlers – GAP | 2YO – GAP | 3-5YO – GAP | School Age – GAP | Current Capacity | Current Enrollment | Difference in slots | Infants-Toddlers – GAP | 2YO – GAP | 3-5YO – GAP | School Age – GAP
(March) |  | 76 |  | n/a | 14 | 54 | 8 |  |  | 95 | 0 | n/a | 16 | 37 | 42 |  |  | 80 | 25 | n/a | 26 | 26 | 28 |  | 112 | 46 | 66 | 8 | 8 | 30 | n/a | 38 | 30 | 8 | 15 | 15 | n/a | n/a
July
August
September
October
December
January
February
March
April
May
June
| Joliet | [7 empty] | Aurora | [7 empty] | Elgin
| Current Capacity | Current Enrollment | Difference in slots | Infants – GAP | Toddlers – GAP | Young PreK GAP | PreK – GAP | School Age – GAP | Current Capacity | Current Enrollment | Difference in slots | Infants – GAP | Toddlers – GAP | Young PreK GAP | PreK – GAP | School Age – GAP | Current Capacity | Current Enrollment | Difference in slots | Infants – GAP | Toddlers – GAP | Young PreK GAP | PreK – GAP | School Age – GAP
(March) |  | 111 |  | 20 | 13 | 15 | 42 | 2 |  | 135 | 77 | 14 | 22 | 14 | 27 | 15 | 222 | 130 | 92 | 8 | 16 | 23 | 45 | 0
July
August
September
October
December
January
February
March
April
May
June

## Budget
Strategy |  | July | August | September | October | November | December | January | February | March | April | May | June
Driect Mail | Expected | 24544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24544 | 0 | 0 | 0
Actual
Difference
Facebook | Expected | 200 | 0 | 0 | 0 | 350 |  | 0 | 0 | 0 | 200 | 0 | 0
Actual
Difference
Google | Expected | 600 |  | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 500 | 500 | 500
Actual
Difference
Parent Referral | Expected | July: 200; October: 200
| Actual | July: 345.95
Difference
Targeting Past Families | Expected
Actual
Difference
Total | Expected | 25544 | 0 | 500 | 700 | 850 | 500 | 500 | 500 | 25144 | 700 | 500 | 500
| Actual | 345.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Difference
Expected Total Cost
Actual Total Cost
Total Difference

## Mailer Planning
Mailer Costs
| Current List | Target Total # | New Addresses to Purchase | Cost for addresses | Cost for per round of mailer (.1539/postcard in FY21) | Cost for three rounds of mailers | Postage Estimate (last time was .137/postcard) | Cost for three rounds of postage | Total Cost Estimate
Edgewater | 3000 | 3833 | 833
Busy Bee | 2700 | 3833 | 1133
Bridgeport | 3500 | 3833 | 333
Aurora | NA | 3833 | 3833
Elgin | NA | 3833 | 3833
Joliet | NA | 3833 | 3833
TOTAL | 9200 | 23000 | 13798
Mailer Demographics
| Address | Mile Radius | Income Level | Children 0-3 | Children 4-7 | Children 8-12 | Chiildren 13-17
Edgewater | 5244 N. Lakewook Ave, Chicago, IL 60640 | 6mi or less from center | 20k-70k | X | X | X
Busy Bee | 2115 Ernie Krueger Cir., Waukegan, IL 60087 | 6mi or less from center | 20k-70k | X | X | X
Bridgeport | 3053 S. Normal Ave., Chicago IL 60616 | 6mi or less from center | 20k-70k | X | X | X
Aurora | 525 College Ave., Aurora, IL 60505 | 6mi or less from center | 20k-70k | X | X | X
Elgin | 210 National Street, Elgin, IL 60120 | 6mi or less from center | 20k-70k | X | X | X
Joliet | 500 Parks Ave., Joliet IL 60432 | 6mi or less from center | 20k-70k | X | X | X
| Total # on list | Drop 1 (Included/Not Included) | Drop 2 (Included/Not Included) | Drop 3 (Included/Not Included) | TOTAL
Edgewater | 3833 | 3833 | 3833 | 3833 | 11499
Busy Bee | 3833 | 3833 | 3833 | 3833 | 11499
Bridgeport | 3833 | 3833 | 3833 | 3833 | 11499
Aurora | 3833 | 0 | 3833 | 3833 | 7666
Elgin | 3833 | 3833 | 3833 | 3833 | 11499
Joliet | 3833 | 0 | 3833 | 3833 | 7666
TOTAL | 23000 | 15332 | 23000 | 23000 | 61328
Mailer Costs ACTUAL | Print/mail | Approx Postage | List Purchase
Pre-Drops
Drop 1 (15331)
Drop 2 (23000)
Drop 3 (23000)
TOTAL
BUDGETED
DIFFERENCE
Last YR Vs This YR | Summer 2020 | Current Campaign
POSTAGE | 0.137 per | 0.131 per
PRINT/MAIL | .1539 per | .1453 per (drops 2+3)
Purchased Addresses | .19 per | .19 per